## Sheet1
| TO DO | DOING | TESTING | DONE | RESPONSIBLE | NEXT DEADLINE (underscore = hard deadline)
GUI | -Add speech recognition -Drive to way points |  | -Implementation with new car model | -Figuring out how to use the app designer -Merge files -Designing the GUI | Arthur, Lennert, Rick
Module 1: Machine Learning | -Finish module 1 in Overleaf | -Work out task 1 in Overleaf |  | -Watch the video lectures -All asignments -Work out task 2 in Overleaf | Ruben, Pieter
Module 2: Speech Recognition | -Work out task 1 in overleaf -Work out task 2 in overleaf | -Make task 2 |  | -Watch the video lectures -Finish task 1 | Ruben, Pieter
Module 3: |  |  | -Verify new car model |  | Arthur, Lennert
Midterm challenge: GUI | -Add randomness to GUI | -Fix braking |  |  | Arthur, Lennert, Rick | 2021-05-11 08:45
Midterm challenge: Speech |  |  |  | -Optimized word selection | Pieter, Ruben | 2021-05-11